KP-RAP PROJECT ¦ DISTRICT TEAM PERFORMANCE REPORT D.I. Khan — Household (Father/Mother) & Girls Survey Activity Enumerator-wise field performance against the daily target of 3 Households per enumerator (3 Father + 3 Mother + 3 Girl interviews = 9 forms/day). Built directly from the raw Household_Survey.csv and Girls_Survey.csv submission records. 7 Enumerators ¦ Field Days: 09-Sep-2026 to 14-Sep-2026 (5 days) ¦ 142 Forms Submitted ¦ Overall Achievement: 60.7%

Target definition: Each enumerator's daily target is 3 Households, meaning 3 Father interviews + 3 Mother interviews + 3 Girl interviews = 9 forms/day/enumerator. Activity window: 09-Sep-2026 to 14-Sep-2026, covering 5 field dates (09-Sep, 10-Sep, 11-Sep, 13-Sep, 14-Sep). No submissions were recorded for 12-Sep-2026, which was used for the Data Quality Session, so it is excluded from the field-day count. Individual targets below are calculated only over the days each enumerator was actually active in the field, so a newly-joined enumerator is not penalised for days before they started.

| ENUMERATORS 7 | FIELD DAYS 5 | TARGET HH 78 | HH COVERED 50 (64.1%) | TARGET FORMS 234 | FORMS SUBMITTED 142 (60.7%) | DAY 1 FIELDED 4/7 |
| --- | --- | --- | --- | --- | --- | --- |

1. Date-Wise District Summary

Har field date par poore district ke liye: kitne enumerators active thay, kitne forms aur households cover huay, aur enumerator-average kitna raha

| Date | Enumerators | Father | Mother | Girls | Target HH | HH Covered | HH % | Target Forms | Total Forms | Forms % | Avg Forms/Enumerator | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 09-Sep-2026 | 4 | 4 | 1 | 6 | 12 | 6 | 50.0% | 36 | 12 | 33.3% | 3.00 | Below Target |
| 10-Sep-2026 | 5 | 9 | 14 | 12 | 15 | 14 | 93.3% | 45 | 35 | 77.8% | 7.00 | Near Target |
| 11-Sep-2026 | 5 | 7 | 12 | 12 | 15 | 12 | 80.0% | 45 | 32 | 71.1% | 6.40 | Near Target |
| 13-Sep-2026 | 5 | 9 | 10 | 10 | 15 | 10 | 66.7% | 45 | 29 | 64.4% | 5.80 | Below Target |
| 14-Sep-2026 | 7 | 9 | 12 | 13 | 21 | 12 | 57.1% | 63 | 34 | 54.0% | 4.86 | Below Target |

12-Sep-2026 is not listed above as it had no field submissions (Data Quality Session day). Across all 5 field dates, D.I. Khan averaged 28.4 forms/day district-wide and covered 50 distinct households in total.

2. First Day Field Deployment — 09-Sep-2026

How many enumerators went to the field on the first day, and how much of the 9-form daily target (3 HH = Father+Mother+Girl) they achieved

| Enumerator (ID) | Fielded? | Father | Mother | Girls | Target HH | HH Covered | HH % | Target Forms | Total Forms | Forms % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Asma Bibi (373641) | Yes | 2 | 0 | 2 | 3 | 2 | 66.7% | 9 | 4 | 44.4% |
| Irum Ikram (373642) | Yes | 1 | 0 | 1 | 3 | 1 | 33.3% | 9 | 2 | 22.2% |
| Javairia (373651) | No | 0 | 0 | 0 | 3 | 0 | 0.0% | 9 | 0 | 0.0% |
| Naureen Khan (373716) | Yes | 0 | 1 | 2 | 3 | 2 | 66.7% | 9 | 4 | 44.4% |
| Shafaq Zahra (373646) | No | 0 | 0 | 0 | 3 | 0 | 0.0% | 9 | 0 | 0.0% |
| Shazia Bibi (373648) | Yes | 1 | 0 | 1 | 3 | 1 | 33.3% | 9 | 2 | 22.2% |
| Shazia begum (373696) | No | 0 | 0 | 0 | 3 | 0 | 0.0% | 9 | 0 | 0.0% |

On 09-Sep, 4 of 7 enumerators were active in the field, submitting 12 forms in total against a combined target of 36 for those fielded (33.3%). The following enumerators had not yet started fieldwork on Day 1 and joined on a later date: Javairia (started 10-Sep), Shafaq Zahra (started 11-Sep), Shazia begum (started 14-Sep).

3. Enumerator-Wise Daily Submissions

Total forms (Father + Mother + Girl) submitted by each enumerator on each field date

| Enumerator | 09-Sep | 10-Sep | 11-Sep | 13-Sep | 14-Sep | Field Days | Total | Avg Forms/Day |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Asma Bibi | 4 | 7 | 5 | 6 | 6 | 5 | 28 | 5.60 |
| Irum Ikram | 2 | 6 | 3 | 6 | 5 | 5 | 22 | 4.40 |
| Javairia | — | 3 | 7 | 6 | 5 | 4 | 21 | 5.25 |
| Naureen Khan | 4 | 5 | — | — | 6 | 3 | 15 | 5.00 |
| Shafaq Zahra | — | — | 6 | 5 | 5 | 3 | 16 | 5.33 |
| Shazia Bibi | 2 | 14 | 11 | 6 | 1 | 5 | 34 | 6.80 |
| Shazia begum | — | — | — | — | 6 | 1 | 6 | 6.00 |

4. Average Form Submission per Day per Enumerator

Total forms submitted divided by the number of days each enumerator was actually in the field, compared with the 9-form daily target

| Enumerator (ID) | Field Days | Daily Target HH | Avg HH/Day | Daily Target Forms | Total Forms | Avg Forms/Day | Avg vs Target | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Shazia Bibi (373648) | 5 | 3 | 2.40 | 9 | 34 | 6.80 | 75.6% | Near Target |
| Shazia begum (373696) | 1 | 3 | 2.00 | 9 | 6 | 6.00 | 66.7% | Below Target |
| Asma Bibi (373641) | 5 | 3 | 2.00 | 9 | 28 | 5.60 | 62.2% | Below Target |
| Shafaq Zahra (373646) | 3 | 3 | 2.00 | 9 | 16 | 5.33 | 59.3% | Below Target |
| Javairia (373651) | 4 | 3 | 2.00 | 9 | 21 | 5.25 | 58.3% | Below Target |
| Naureen Khan (373716) | 3 | 3 | 2.00 | 9 | 15 | 5.00 | 55.6% | Below Target |
| Irum Ikram (373642) | 5 | 3 | 1.60 | 9 | 22 | 4.40 | 48.9% | Below Target |

5. Overall Performance vs Target

Cumulative Father / Mother / Girl forms achieved against the cumulative target (9 forms x field days worked) for the full activity period

| Enumerator (ID) | Field Days | Target HH | HH Covered | HH % | Target Forms | Father | Mother | Girls | Total Forms | Forms % | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Shazia Bibi (373648) | 5 | 15 | 12 | 80.0% | 45 | 9 | 12 | 13 | 34 | 75.6% | Near Target |
| Shazia begum (373696) | 1 | 3 | 2 | 66.7% | 9 | 2 | 2 | 2 | 6 | 66.7% | Below Target |
| Asma Bibi (373641) | 5 | 15 | 10 | 66.7% | 45 | 9 | 9 | 10 | 28 | 62.2% | Below Target |
| Shafaq Zahra (373646) | 3 | 9 | 6 | 66.7% | 27 | 3 | 6 | 6 | 16 | 59.3% | Below Target |
| Javairia (373651) | 4 | 12 | 8 | 66.7% | 36 | 5 | 8 | 8 | 21 | 58.3% | Below Target |
| Naureen Khan (373716) | 3 | 9 | 6 | 66.7% | 27 | 3 | 5 | 6 | 15 | 55.6% | Below Target |
| Irum Ikram (373642) | 5 | 15 | 8 | 53.3% | 45 | 7 | 7 | 8 | 22 | 48.9% | Below Target |

6. District Summary

Key observations for the field team lead / district coordinator

Across 7 enumerators and 5 field dates (09-Sep-2026 to 14-Sep-2026), D.I. Khan covered 50 households against a targeted 78 households (64.1%), and submitted 142 forms against a targeted 234 forms (60.7% overall achievement). Shazia Bibi has the highest achievement rate at 75.6% of target, while Irum Ikram has the lowest at 48.9%. 6 enumerator(s) are currently below 70% of their target and should be prioritised for field coaching / follow-up: Asma Bibi, Irum Ikram, Javairia, Naureen Khan, Shafaq Zahra, Shazia begum.

7. Key Insights & Recommendations

Performance ka mukammal khulasa — kya achha hua, kahan gap hai, aur agay kya karna hai

Overall performance: D.I. Khan achieved 60.7% of its total form target (142 of 234 forms) and 64.1% of its household target (50 of 78 HH) over 5 field days. District-wide the team averaged 28.4 forms/day and 10.0 HH/day, against the per-enumerator daily target of 9 forms (3 HH).

Field ramp-up: only 4 of 7 enumerators were in the field on Day 1 (09-Sep), achieving 33.3% of that day's target. The remaining 3 joined progressively between 10-Sep and 14-Sep, which is the main reason district-wide totals rose in the days after Day 1.

Best vs. weakest day: 10-Sep-2026 was the strongest day at 77.8% of that day's target (35 forms from 5 enumerators), while 09-Sep-2026 was the weakest at 33.3% (12 forms from 4 enumerators).

Father vs. Mother vs. Girl forms: 38 Father, 49 Mother and 53 Girl forms were submitted in total. Father interviews are running behind Mother interviews by 11 forms district-wide, suggesting fathers are harder to reach/available less often during field visits — worth flagging to the team as a scheduling issue.

Household completion: of the 50 households visited, 35 have both Father and Mother interviews completed, while 15 still have only one parent interviewed and need a revisit to close out the household.

Team consistency: 3 enumerator(s) worked all 5 field days (Asma Bibi, Irum Ikram, Shazia Bibi), while 4 worked only part of the period (Javairia (4d), Naureen Khan (3d), Shafaq Zahra (3d), Shazia begum (1d)). Achievement figures above are already calculated only over each person's own active days, so this is for staffing awareness rather than a performance penalty.

Needs follow-up: 6 of 7 enumerators are below 70% of their individual target — Asma Bibi, Irum Ikram, Javairia, Naureen Khan, Shafaq Zahra, Shazia begum. Recommend the district coordinator review daily plans with them and confirm no access/availability issues are limiting household visits.

KP-RAP M&E  |  District Team Performance Report  |  D.I. Khan

Source: Surveys/Household_Survey.csv (respondent field: 1=Father, 2=Mother, 3/blank=Other) and Surveys/Girls_Survey.csv. Naureen Khan's two Enumerator IDs (373716 and 453925) are combined as one enumerator.