KPRAP Tracking and Survey Protocol

1. Purpose and Background

The KPRAP Impact Evaluation requires high-quality data from approximately 4,038 fully completed households across 4 districts in Khyber Pakhtunkhwa. Achieving this depends critically on how tracking is designed and executed before the household survey begins.

Past field experience has shown that attrition between tracking and survey can compromise the sample size. This protocol consolidates the latest decisions taken with the AoE and PIU and address the risk of attrition through over-tracking, clear completion definitions, and tight control on revisits and replacements.

2. Guiding Principle: Front-Load Effort During Tracking

The core idea is simple: track slightly more households upfront to reduce the chances of AOE having to return to the tracking stage if the Household sample target is not met during survey. If the sample target is missed during survey, AOE would need to remobilize field teams for an additional tracking round — incurring higher costs than the modest upfront cost of over-tracking now. Over-tracking, scheduling interviews during tracking visits, and verifying contact details  make the survey stage almost mechanical, reducing the chances of falling short of the 4,038 HH sample target.

Track at approximately 120% of the target sample to create a buffer for unavoidable losses.

Enumerators must work through all 4,860 assigned girls to track — not stop once a quota is met.

Replacements during the HH survey come only from the over-tracked pool — no fresh listing or backtracking during survey. The over tracking will allow that there is a very little chance of team going back to the field for tracking if the sample target of 4038 is not met.

3. Tracking Protocol

3.1 Coverage Requirements

Enumerators must attempt every household on their assigned list, including alternates.

Primary respondents must be attempted first. Alternates are used after primaries have been exhausted.

All informed contacts (e.g., neighbors, LHWs, imams) approached during tracking must be recorded — these will be used for back-check calls.

Enumerators should be informed in advance that back-checks will occur, which reinforces data quality discipline.

3.2 What Counts as 'Tracked'

A household is considered tracked under the following conditions:

Structure verified and respondent contact made (ideal outcome: counted as ‘Tracked’).

Structure verified but respondent unavailable — 3 revisits required. This can be combined with next day visit around that same catchment.

Structure cannot be located after due diligence (checks with neighbors, LHW, imam) — no revisit required.

4. Transition from Tracking to Survey

Once tracking is complete in a district, a fixed survey sample is drawn from the successfully tracked households. Not all tracked households proceed to survey — the additional ones form a controlled replacement pool in case the cluster/catchment target is not met. The overall sample for HH survey will remain at 4038.

Survey sample is locked before household survey begins in that district.

Enumerators should not approach replacement households unless an originally selected household has fully failed (after all revisits).

5. Definition of the Completed Sample (N)

Making the definition of N explicit is critical. The target of approximately 4,038 households refers to fully completed cases — not merely households that were visited or partially surveyed.

| Outcome | Counts toward N? | Notes |
| --- | --- | --- |
| Girl interviewed AND tested | Yes (required) | Non-negotiable; girl's survey is the most important component. 3 revisits required to interview the girl |
| Mother interviewed | Yes (required) | Mother's survey is the second core component. 3 revisits required to interview mother |
| Father interviewed | Yes | Counts when achieved within the allowed revisit attempts. 1 revisit required to interview father |
| Father not found after 1 revisit attempt | Yes | Case is still considered complete if girl and mother are done. |
| Girl not interviewed or not tested | No | Case cannot be marked complete without the girl component. 3 Revisits required |
| Mother not interviewed | No | Case cannot be marked complete without the mother component. 3 Revisits required |
| Refusal (any core respondent) | No | Recorded but excluded from N. |
| Not at home / unavailable across all visits | No | Recorded but excluded from N. |
| Failure to track (structure not found) | No | Recorded; replacement may be drawn from tracked pool. |

Why this matters Field teams and the survey firm must clearly understand that partial completions do not count toward the target N.

6. Revisit Rules

Revisits are tightly controlled to balance data quality with field cost. The rules differ between the tracking stage and the survey stage.

| Stage | Situation | Max attempts | Rule |
| --- | --- | --- | --- |
| Tracking | Structure not found after checks with neighbors/LHW | 0 | Mark as untraceable; no revisit required. |
| Tracking | Structure found, respondent unavailable | Up to 3 | Revisit on different days/times; capture availability. |
| Survey | Girl interview pending | Up to 3 | Girl interview is mandatory for case completion. |
| Survey | Mother interview pending | Up to 3 | Mother interview is mandatory for case completion. |
| Survey | Father interview pending | 1 | Limited effort; case still counts if exhausted without success. |
| Survey | All core respondents failed after revisits | — | Replace with a household from the tracked pool. |

Note 1: revisits should be planned on different days and times of day to maximize the chance of finding respondents, particularly fathers and working household members.

Note 2: One revisit is required specifically to interview the father, provided the mother and girl have already been surveyed. However, if the team makes a revisit to find the mother and/or girl, and the father is present during that visit, his interview should also be conducted at that time.

8. Monitoring and Adaptive Top-Up

After the initial tracking round, the WB/PIU team will assess how close the tracked sample is to the required N. This requires a buffer of 2 days after completion of tracking in each district. If a shortfall is detected, additional households can be assigned for tracking, but only with explicit instruction from the PIU/WB team.

Review tracking outcomes by district and cluster to identify gaps early.

If shortfall is detected, assign top-up tracking from the remaining listing before survey closes in that district.

Flag clusters where the listing itself appears too thin so they can be addressed during the survey round (combined tracking + survey visit).

9. Quality Control and Back-Checks

Back-check calls by a third party firm hired by WB will be made to a random sample of tracked households using the recorded contact numbers.

Calls will also be made to key informants (neighbors, LHW, imam) listed during tracking to verify that the enumerator actually visited.

Enumerators must be informed in advance that back-checks will take place

Any inconsistencies trigger a supervisor review and, if needed, a revisit by a different enumerator.