KP-RAP PROJECT ¦ DISTRICT TEAM PERFORMANCE REPORT Hangu — Household (Father/Mother) & Girls Survey Activity Enumerator-wise field performance against the daily target of 3 Households per enumerator (3 Father + 3 Mother + 3 Girl interviews = 9 forms/day). Built directly from the raw Household_Survey.csv and Girls_Survey.csv submission records. 4 Enumerators ¦ Field Days: 09-Sep-2026 to 14-Sep-2026 (5 days) ¦ 78 Forms Submitted ¦ Overall Achievement: 57.8%

Target definition: Each enumerator's daily target is 3 Households, meaning 3 Father interviews + 3 Mother interviews + 3 Girl interviews = 9 forms/day/enumerator. Activity window: 09-Sep-2026 to 14-Sep-2026, covering 5 field dates (09-Sep, 10-Sep, 11-Sep, 13-Sep, 14-Sep). No submissions were recorded for 12-Sep-2026, which was used for the Data Quality Session, so it is excluded from the field-day count. Individual targets below are calculated only over the days each enumerator was actually active in the field, so a newly-joined enumerator is not penalised for days before they started.

| ENUMERATORS 4 | FIELD DAYS 5 | TARGET HH 45 | HH COVERED 33 (73.3%) | TARGET FORMS 135 | FORMS SUBMITTED 78 (57.8%) | DAY 1 FIELDED 1/4 |
| --- | --- | --- | --- | --- | --- | --- |

1. Date-Wise District Summary

Har field date par poore district ke liye: kitne enumerators active thay, kitne forms aur households cover huay, aur enumerator-average kitna raha

| Date | Enumerators | Father | Mother | Girls | Target HH | HH Covered | HH % | Target Forms | Total Forms | Forms % | Avg Forms/Enumerator | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 09-Sep-2026 | 1 | 0 | 1 | 1 | 3 | 1 | 33.3% | 9 | 2 | 22.2% | 2.00 | Below Target |
| 10-Sep-2026 | 3 | 1 | 8 | 6 | 9 | 9 | 100.0% | 27 | 16 | 59.3% | 5.33 | Below Target |
| 11-Sep-2026 | 3 | 4 | 2 | 5 | 9 | 5 | 55.6% | 27 | 11 | 40.7% | 3.67 | Below Target |
| 13-Sep-2026 | 4 | 3 | 7 | 8 | 12 | 8 | 66.7% | 36 | 18 | 50.0% | 4.50 | Below Target |
| 14-Sep-2026 | 4 | 7 | 10 | 11 | 12 | 13 | 108.3% | 36 | 31 | 86.1% | 7.75 | Near Target |

12-Sep-2026 is not listed above as it had no field submissions (Data Quality Session day). Across all 5 field dates, Hangu averaged 15.6 forms/day district-wide and covered 33 distinct households in total.

2. First Day Field Deployment — 09-Sep-2026

How many enumerators went to the field on the first day, and how much of the 9-form daily target (3 HH = Father+Mother+Girl) they achieved

| Enumerator (ID) | Fielded? | Father | Mother | Girls | Target HH | HH Covered | HH % | Target Forms | Total Forms | Forms % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Laiba Shams (373706) | No | 0 | 0 | 0 | 3 | 0 | 0.0% | 9 | 0 | 0.0% |
| Mahnoor (373705) | Yes | 0 | 1 | 1 | 3 | 1 | 33.3% | 9 | 2 | 22.2% |
| Nadia bibi (373669) | No | 0 | 0 | 0 | 3 | 0 | 0.0% | 9 | 0 | 0.0% |
| Summiya Hayat (373710) | No | 0 | 0 | 0 | 3 | 0 | 0.0% | 9 | 0 | 0.0% |

On 09-Sep, 1 of 4 enumerators were active in the field, submitting 2 forms in total against a combined target of 9 for those fielded (22.2%). The following enumerators had not yet started fieldwork on Day 1 and joined on a later date: Laiba Shams (started 10-Sep), Nadia bibi (started 10-Sep), Summiya Hayat (started 11-Sep).

3. Enumerator-Wise Daily Submissions

Total forms (Father + Mother + Girl) submitted by each enumerator on each field date

| Enumerator | 09-Sep | 10-Sep | 11-Sep | 13-Sep | 14-Sep | Field Days | Total | Avg Forms/Day |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Laiba Shams | — | 5 | 5 | 5 | 6 | 4 | 21 | 5.25 |
| Mahnoor | 2 | 5 | 4 | 5 | 9 | 5 | 25 | 5.00 |
| Nadia bibi | — | 6 | — | 4 | 9 | 3 | 19 | 6.33 |
| Summiya Hayat | — | — | 2 | 4 | 7 | 3 | 13 | 4.33 |

4. Average Form Submission per Day per Enumerator

Total forms submitted divided by the number of days each enumerator was actually in the field, compared with the 9-form daily target

| Enumerator (ID) | Field Days | Daily Target HH | Avg HH/Day | Daily Target Forms | Total Forms | Avg Forms/Day | Avg vs Target | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Nadia bibi (373669) | 3 | 3 | 2.67 | 9 | 19 | 6.33 | 70.4% | Near Target |
| Laiba Shams (373706) | 4 | 3 | 2.25 | 9 | 21 | 5.25 | 58.3% | Below Target |
| Mahnoor (373705) | 5 | 3 | 2.00 | 9 | 25 | 5.00 | 55.6% | Below Target |
| Summiya Hayat (373710) | 3 | 3 | 2.00 | 9 | 13 | 4.33 | 48.1% | Below Target |

5. Overall Performance vs Target

Cumulative Father / Mother / Girl forms achieved against the cumulative target (9 forms x field days worked) for the full activity period

| Enumerator (ID) | Field Days | Target HH | HH Covered | HH % | Target Forms | Father | Mother | Girls | Total Forms | Forms % | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Nadia bibi (373669) | 3 | 9 | 8 | 88.9% | 27 | 3 | 8 | 8 | 19 | 70.4% | Near Target |
| Laiba Shams (373706) | 4 | 12 | 9 | 75.0% | 36 | 4 | 7 | 8 | 21 | 58.3% | Below Target |
| Mahnoor (373705) | 5 | 15 | 10 | 66.7% | 45 | 6 | 7 | 10 | 25 | 55.6% | Below Target |
| Summiya Hayat (373710) | 3 | 9 | 6 | 66.7% | 27 | 2 | 6 | 5 | 13 | 48.1% | Below Target |

6. District Summary

Key observations for the field team lead / district coordinator

Across 4 enumerators and 5 field dates (09-Sep-2026 to 14-Sep-2026), Hangu covered 33 households against a targeted 45 households (73.3%), and submitted 78 forms against a targeted 135 forms (57.8% overall achievement). Nadia bibi has the highest achievement rate at 70.4% of target, while Summiya Hayat has the lowest at 48.1%. 3 enumerator(s) are currently below 70% of their target and should be prioritised for field coaching / follow-up: Laiba Shams, Mahnoor, Summiya Hayat.

7. Key Insights & Recommendations

Performance ka mukammal khulasa — kya achha hua, kahan gap hai, aur agay kya karna hai

Overall performance: Hangu achieved 57.8% of its total form target (78 of 135 forms) and 73.3% of its household target (33 of 45 HH) over 5 field days. District-wide the team averaged 15.6 forms/day and 6.6 HH/day, against the per-enumerator daily target of 9 forms (3 HH).

Field ramp-up: only 1 of 4 enumerators were in the field on Day 1 (09-Sep), achieving 22.2% of that day's target. The remaining 3 joined progressively between 10-Sep and 11-Sep, which is the main reason district-wide totals rose in the days after Day 1.

Best vs. weakest day: 14-Sep-2026 was the strongest day at 86.1% of that day's target (31 forms from 4 enumerators), while 09-Sep-2026 was the weakest at 22.2% (2 forms from 1 enumerator).

Father vs. Mother vs. Girl forms: 15 Father, 28 Mother and 31 Girl forms were submitted in total. Father interviews are running behind Mother interviews by 13 forms district-wide, suggesting fathers are harder to reach/available less often during field visits — worth flagging to the team as a scheduling issue.

Household completion: of the 33 households visited, 14 have both Father and Mother interviews completed, while 19 still have only one parent interviewed and need a revisit to close out the household.

Team consistency: 1 enumerator(s) worked all 5 field days (Mahnoor), while 3 worked only part of the period (Laiba Shams (4d), Nadia bibi (3d), Summiya Hayat (3d)). Achievement figures above are already calculated only over each person's own active days, so this is for staffing awareness rather than a performance penalty.

Needs follow-up: 3 of 4 enumerators are below 70% of their individual target — Laiba Shams, Mahnoor, Summiya Hayat. Recommend the district coordinator review daily plans with them and confirm no access/availability issues are limiting household visits.

KP-RAP M&E  |  District Team Performance Report  |  Hangu

Source: Surveys/Household_Survey.csv (respondent field: 1=Father, 2=Mother, 3/blank=Other) and Surveys/Girls_Survey.csv. Naureen Khan's two Enumerator IDs (373716 and 453925) are combined as one enumerator.